## Risk Management Matrix
RISK MANAGEMENT MATRIX
NAME | ECG SMARTWATCH PROJECT |  |  |  | OBJECTIVE |  |  |  | DELIVER RISK CONTROL PLAN AND DESIRED ACTIONS, AT DESIGN REPORT RELEASE
REF/ID | PRE-MITIGATION |  |  |  | TYPE | ASSIGNED OWNER | DUE DATE | ACTION ID | MITIGATIONS / WARNINGS / REMEDIES | POST-MITIGATION |  |  |  | RISK SEVERITY KEY | RISK LIKELIHOOD KEY | RISK LEVEL KEY | ACCEPTABLE TO PROCEED? KEY
ID | RISK | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | TIMING / TECHNICAL / COST / RESOURCE AND SKILLS / REGULATORY / PROCESS / COMMUNICATION / ORGANISATION |  |  |  |  | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | ACCEPTABLE TO PROCEED?
ECGSM_01 | BATTERY AUTONOMY | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | POWER USAGE TEAM | 2021-04-01 | ECG_ACT_01 | CONSUMPTION SIMULATION, BENCHMARK | unDESIRABLE | POSSIBLE | MEDIUM | YES | ACCEPTABLE | IMPROBABLE | LOW | YES
ECGSM_02 | LACK OF VALIDATION TESTING | TOLERABLE | POSSIBLE | HIGH | TIMING | VALIDATION TEAM | 2021-04-01 | ECG_ACT_02 | INCLUDE VALIDATION PLAN | TOLERABLE | IMPROBABLE | LOW | YES | TOLERABLE | POSSIBLE | MEDIUM | NO
ECGSM_03 | HOUSING NOT WATERPROOF | UNDESIRABLE | PROBABLE | HIGH | TECHNICAL | MECHANICAL TEAM | 2021-04-01 | ECG_ACT_03 | IMPROVED SEALING DESIGN | UNDESIRABLE | IMPROBABLE | LOW | YES | UNDESIRABLE | PROBABLE | HIGH
ECGSM_04 | FITNESS DATA PRIVACY | INTOLERABLE | PROBABLE | EXTREME | REGULATORY | LEGAL TEAM | 2020-12-18 | ECG_ACT_04 | ENSURE SAFE ENCRYPTING OF DATA STORAGE | INTOLERABLE | POSSIBLE | MEDIUM | YES | INTOLERABLE |  | EXTREME
ECGSM_05 | WATCH SIZE NOT FITTING | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | MECHANICAL TEAM | 2020-12-18 | ECG_ACT_05 | BENCHMARK AVERAGE USER WRIST SIZE | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_06 | CHARGER MONITORING FAILURE LEADING TO BATTERY OVERVOLTAGE | INTOLERABLE | POSSIBLE | EXTREME | SAFETY | POWER MANAGEMENT TEAM | 2020-12-18 | ECG_ACT_06 | ADD OVERVOLTAGE CHARGIN PROTECTION | INTOLERABLE | IMPROBABLE | HIGH
ECGSM_07 | POWER MONITORING: FAST BATTERY SOC DEPLETION | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | POWER MANAGEMENT TEAM | 2020-12-18 | ECG_ACT_07 | ADJUST DISPLAY TIME STRATEGY | UNDESIRABLE | POSSIBLE | HIGH
ECGSM_08 | ACUTATOR LINEAR VIBRATION: MOTOR NOT OPERATING | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | HARDWARE TEAM | 2020-12-18 | ECG_ACT_08 | RELIABILITY TESTING | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_09 | ACUTATOR LINEAR VIBRATION: MOTOR OPERATING ERRONEOUSLY | INTOLERABLE | POSSIBLE | EXTREME | TECHNICAL | HARDWARE TEAM | 2020-12-18 | ECG_ACT_09 | VALIDATION PLAN | INTOLERABLE | IMPROBABLE | HIGH
ECGSM_10 | STORAGE: DATA NOT STORED (POSITION, MAP) | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | SYSTEM TEAM | 2020-12-18 | ECG_ACT_10 | VALIDATION PLAN | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_11 | SENSOR - CUSTOMER ERRONEOUSLY ALARMED BY HEART RATE INFORMATION TOO HIGH | INTOLERABLE | PROBABLE | EXTREME | TECHNICAL | SYSTEM TEAM | 2020-12-11 | ECG_ACT_11 | VALIDATION PLAN | INTOLERABLE | POSSIBLE | HIGH
ECGSM_12 | SENSOR - CUSTOMER ERRONEOUSLY ALARMED BY HEART RATE INFORMATION TOO HIGH | INTOLERABLE | PROBABLE | EXTREME | TECHNICAL | SYSTEM TEAM | 2020-12-11 | ECG_ACT_12 | VALIDATION PLAN | INTOLERABLE | POSSIBLE | HIGH
ECGSM_13 | SENSOR - CUSTOMER ERRONEOUSLY ALARMED BY SP2 INFORMATION TOO HIGH | UNDESIRABLE | PROBABLE | HIGH | TECHNICAL | SYSTEM TEAM | 2020-12-11 | ECG_ACT_13 | VALIDATION PLAN | UNDESIRABLE | POSSIBLE | HIGH
ECGSM_14 | SENSOR - CUSTOMER ERRONEOUSLY ALARMED BY SP2 INFORMATION TOO HIGH | UNDESIRABLE | PROBABLE | HIGH | TECHNICAL | SYSTEM TEAM | 2020-12-11 | ECG_ACT_14 | VALIDATION PLAN | UNDESIRABLE | POSSIBLE | HIGH
ECGSM_15 | SENSOR - 3 AXIS ACCELEROMETER - SENSITIVITY TO MOTION TOO LOW | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | SYSTEM TEAM | 2020-12-11 | ECG_ACT_15 | VALIDATION PLAN | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_16 | SENSOR - 3 AXIS ACCELEROMETER - SENSITIVITY TO MOTION TOO HIGH | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | SYSTEM TEAM | 2020-12-11 | ECG_ACT_16 | VALIDATION PLAN | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_17 | SENSOR - ECG - INTERMITTENT FAILURE TO CAPTURE | INTOLERABLE | POSSIBLE | EXTREME | TECHNICAL | HARDWARE TEAM | 2020-12-11 | ECG_ACT_17 | VALIDATION AND TESTING OF CAPTURE THRESHOLD ON DATABASE CARDIAC MALFUNCTION, METABOLIC ABNORMALITIES AND OR DRUGS IMPACTS | INTOLERABLE | IMPROBABLE | HIGH
ECGSM_18 | SENSOR - ECG - OVERSENSING CAPTURE FAILURE | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | HARDWARE TEAM | 2020-12-11 | ECG_ACT_18 | VALIDATION PLAN | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_19 | SENSOR - GPS RECEIVER SIGNAL INTERFERENCE | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | HARDWARE TEAM | 2020-12-11 | ECG_ACT_19 | VALIDATION AND TESTING ON URBAN, DENSE AREA | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_20 | SENSOR - GPS SIGNAL SPOOFING | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | HARDWARE TEAM | 2020-12-11 | ECG_ACT_20 | VALIDATION PLAN | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_21 | CAPACITIVE TOUCH OLED DISPLAY: not operating | INTOLERABLE | POSSIBLE | EXTREME | TECHNICAL | HARDWARE TEAM | 2020-12-11 | ECG_ACT_21 | VALIDATION PLAN | INTOLERABLE | IMPROBABLE | HIGH
ECGSM_22 | CAPACITIVE TOUCH OLED DISPLAY: intermittent display | INTOLERABLE | POSSIBLE | EXTREME | TECHNICAL | HARDWARE TEAM | 2020-12-11 | ECG_ACT_22 | VALIDATION PLAN | INTOLERABLE | IMPROBABLE | HIGH
ECGSM_23 | CAPACITIVE TOUCH OLED DISPLAY: operating intempestively | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | HARDWARE TEAM | 2020-12-11 | ECG_ACT_23 | IDENTIFY ADDITIONAL PROJECT TEAM | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_24 | BLUETOOTH MODULE - FAILURE TO PAIR WITH MOBILE DEVICE | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | SW TEAM | 2020-12-11 | ECG_ACT_24 | VALIDATION PLAN | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_25 | BLUETOOTH MODULE - FAILURE TO UPLOAD DATA TO MOBILE DEVICE | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | SW TEAM | 2020-12-11 | ECG_ACT_25 | VALIDATION PLAN | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_26 | BLUETOOTH MODULE - FAILURE TO DOWNLOAD DATA FROM MOBILE DEVICE | UNDESIRABLE | POSSIBLE | HIGH | TECHNICAL | SW TEAM | 2020-12-11 | ECG_ACT_26 | DEFINE USE CYCLES FOR MISSION PROFILE | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
ECGSM_27 | BUTTON SENSOR NOT OPERATING: USER INPUT NOT DETECTED | INTOLERABLE | POSSIBLE | EXTREME | TECHNICAL | SW TEAM | 2020-12-11 | ECG_ACT_27 | VALIDATION PLAN | INTOLERABLE | IMPROBABLE | HIGH
ECGSM_28 | STAFF AVAILABILITY AFTER REPORT DELIVERY | TOLERABLE | PROBABLE | HIGH | RESOURCE | MANAGEMENT | 2020-12-11 | ECG_ACT_28 | FUND RAISING | TOLERABLE | POSSIBLE | MEDIUM | YES

## Annex
LEGEND
Technical Risk | Confidence that a particular requirement is achievable given the constraint of existing technology.
Supply Chain | Problem easily procuring high-quality materials and parts for our prototype and/or production units
Manufacturability risks | Producing prototype components and assemblies quickly and reliably enough to meet the schedule and project expense objectives? Reliability?
Unit Cost | Product at or below the budgeted cost of goods? Is our customer’s Total Cost of Ownership going to fit within their budget?
Product fit/Market | Will our potential customers like what we are producing and pay us enough for it?
Resource Risks | Resources to meet the schedule target? What if a key person leaves the company or gets hit by the proverbial beer truck?
Program-management | Major scope-change during the project.
Interpersonal | lack of effective communication between members of the development team, or between the team and management.
Regulatory | Regulations we’ll need to meet, and how will we gain our regulatory approvals with a minimum delay of our launch?
Unknown risks
Experience
Power supply operation
Static and Dynamic characteristics
Hardware Description Language
Choice of SW programming language
support for devices used
Program paradigm to follow
Experience